## Plan
ID | Phase | Workstream | Task Name | Environment | Duration (workdays) | Start | End | Depends On (ID) | Owner | Status | % Complete | Milestone | Notes
1 | Phase 1 – Data Clean Up | Preliminary Work | Provide backup of Sylvan PROD database | PROD | 1 | 2025-08-25 | 2025-08-25 |  |  | Not Started | 0 | No
2 | Phase 1 – Data Clean Up | Preliminary Work | Send Sylvan PROD DB extract to SS&C | PROD | 1 | 2025-08-26 | 2025-08-26 | 1 |  | Not Started | 0 | No
3 | Phase 1 – Data Clean Up | Preliminary Work | Install SQL Server and add all users to Sylvan DEV DB | DEV | 2 | 2025-08-27 | 2025-08-28 | 2 |  | Not Started | 0 | No
4 | Phase 1 – Data Clean Up | Restore PROD data extract → DEV | Submit request to restore/load PROD data extract into DEV Sylvan DB | DEV | 1 | 2025-08-29 | 2025-08-29 | 3 |  | Not Started | 0 | No
5 | Phase 1 – Data Clean Up | Restore PROD data extract → DEV | Restore/Load PROD data extract into DEV Sylvan DB | DEV | 2 | 2025-09-01 | 2025-09-02 | 4 |  | Not Started | 0 | No
6 | Phase 1 – Data Clean Up | Prep & Testing | Check out data in Sylvan DEV DB | DEV | 1 | 2025-09-03 | 2025-09-03 | 5 |  | Not Started | 0 | No
7 | Phase 1 – Data Clean Up | Prep & Testing | Install Sylvan 7.6 upgrade on DEV Sylvan App Server | DEV | 1 | 2025-09-04 | 2025-09-04 | 6 |  | Not Started | 0 | No
8 | Phase 1 – Data Clean Up | Prep & Testing | Hand off Sylvan DEV DB for functional testing (to Jason & team) | DEV | 1 | 2025-09-05 | 2025-09-05 | 7 |  | Not Started | 0 | No
9 | Phase 1 – Data Clean Up | Prep & Testing | Functional testing & cleanup (users, portfolios, indexes) | DEV | 5 | 2025-09-08 | 2025-09-12 | 8 |  | Not Started | 0 | No
10 | Phase 1 – Data Clean Up | Environment Clean Up | Build & test scripts to clean up users | DEV | 3 | 2025-09-15 | 2025-09-17 | 9 |  | Not Started | 0 | No
11 | Phase 1 – Data Clean Up | Environment Clean Up | Build & test scripts/process to remove class level portfolio results | DEV | 2 | 2025-09-18 | 2025-09-19 | 10 |  | Not Started | 0 | No
12 | Phase 1 – Data Clean Up | Environment Clean Up | Build & test scripts/process to remove class level index results | DEV | 2 | 2025-09-22 | 2025-09-23 | 11 |  | Not Started | 0 | No
13 | Phase 1 – Data Clean Up | Environment Clean Up | Deliver final package | DEV | 1 | 2025-09-24 | 2025-09-24 | 12 |  | Not Started | 0 | No
14 | Phase 1 – Data Clean Up | Environment Clean Up | Apply in UAT and PROD | UAT/PROD | 2 | 2025-09-25 | 2025-09-26 | 13 |  | Not Started | 0 | No
15 | Phase 2 – Upgrade | Preliminary Work | Run upgrade scripts | DEV | 1 | 2025-09-29 | 2025-09-29 | 14 |  | Not Started | 0 | No
16 | Phase 2 – Upgrade | Preliminary Work | Troubleshoot any issue with DEV | DEV | 2 | 2025-09-30 | 2025-10-01 | 15 |  | Not Started | 0 | No
17 | Phase 2 – Upgrade | Preliminary Work | Update scripts to use one common total-level hierarchy for indices | DEV | 2 | 2025-10-02 | 2025-10-03 | 16 |  | Not Started | 0 | No
18 | Phase 2 – Upgrade | Conversion Build | Build scripts to convert floating-weight benchmark to new functionality | DEV | 3 | 2025-10-06 | 2025-10-08 | 17 |  | Not Started | 0 | No
19 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Build application server | DEV | 2 | 2025-10-09 | 2025-10-10 | 18 |  | Not Started | 0 | No
20 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Install software | DEV | 1 | 2025-10-13 | 2025-10-13 | 19 |  | Not Started | 0 | No
21 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Build latest DB and run upgrade scripts | DEV | 2 | 2025-10-14 | 2025-10-15 | 20 |  | Not Started | 0 | No
22 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Get SS&C assistance (as needed) | DEV | 1 | 2025-10-16 | 2025-10-16 | 21 |  | Not Started | 0 | No
23 | Phase 2 – Upgrade | Update Custom Reports | Send updated list of stored procedures to SS&C for confirmation | DEV | 1 | 2025-10-17 | 2025-10-17 | 22 |  | Not Started | 0 | No
24 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_port_bench_asof_wrp | DEV | 2 | 2025-10-20 | 2025-10-21 | 23 |  | Not Started | 0 | No
25 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_load_memPortBM_PerRolling | DEV | 2 | 2025-10-22 | 2025-10-23 | 24 |  | Not Started | 0 | No
26 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_load_cpfactual_mlt | DEV | 2 | 2025-10-24 | 2025-10-27 | 25 |  | Not Started | 0 | No
27 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_load_composite_monthly | DEV | 2 | 2025-10-28 | 2025-10-29 | 26 |  | Not Started | 0 | No
28 | Phase 2 – Upgrade | Training | Training on like-for-like processes | All | 2 | 2025-10-30 | 2025-10-31 | 27 |  | Not Started | 0 | No
29 | Phase 2 – Upgrade | Training | Training on new functionality (focus on pain points) | All | 2 | 2025-11-03 | 2025-11-04 | 28 |  | Not Started | 0 | No
30 | Phase 2 – Upgrade | User Testing | UAT – run through test scripts | UAT | 5 | 2025-11-05 | 2025-11-11 | 29 |  | Not Started | 0 | No
31 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Update new application server with FIRMRun, Java 21, Autosys | PROD | 2 | 2025-11-12 | 2025-11-13 | 30 |  | Not Started | 0 | No
32 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Reserve Windows 10 boxes for PR team (contingency for Go-Live) | PROD | 1 | 2025-11-14 | 2025-11-14 | 31 |  | Not Started | 0 | No
33 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Update test plan based on Jason's scripts; share with QA | PROD | 2 | 2025-11-17 | 2025-11-18 | 32 |  | Not Started | 0 | No
34 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Setup DB server with SQL Server and supporting software (PROD) | PROD | 2 | 2025-11-19 | 2025-11-20 | 33 |  | Not Started | 0 | No
35 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Setup application server with FIRMRun, Java 21, Autosys (PROD) | PROD | 2 | 2025-11-21 | 2025-11-24 | 34 |  | Not Started | 0 | No
36 | Phase 2 – Upgrade | Parallel Run & Testing | Run processes in parallel | PROD | 5 | 2025-11-25 | 2025-12-01 | 35 |  | Not Started | 0 | No
37 | Phase 2 – Upgrade | Parallel Run & Testing | Provide support as needed (parallel run window) | PROD | 5 | 2025-12-02 | 2025-12-08 | 36 |  | Not Started | 0 | No
38 | Phase 2 – Upgrade | Go Live | Restore test DB on new PROD environment & run upgrade scripts | PROD | 1 | 2025-12-09 | 2025-12-09 | 37 |  | Not Started | 0 | Yes
39 | Phase 2 – Upgrade | Go Live | Go-Live support | PROD | 3 | 2025-12-10 | 2025-12-12 | 38 |  | Not Started | 0 | No
40 | Phase 2 – Upgrade | Post Go Live Support | Hypercare / support for up to 4 weeks post Go-Live | PROD | 20 | 2025-12-15 | 2026-01-09 | 39 |  | Not Started | 0 | No

## Gantt
Task | Start Offset | Duration
Provide backup of Sylvan PROD database | 0 | 1
Send Sylvan PROD DB extract to SS&C | 1 | 1
Install SQL Server and add all users to Sylvan DEV DB | 2 | 2
Submit request to restore/load PROD data extract into DEV Sylvan DB | 4 | 1
Restore/Load PROD data extract into DEV Sylvan DB | 7 | 2
Check out data in Sylvan DEV DB | 9 | 1
Install Sylvan 7.6 upgrade on DEV Sylvan App Server | 10 | 1
Hand off Sylvan DEV DB for functional testing (to Jason & team) | 11 | 1
Functional testing & cleanup (users, portfolios, indexes) | 14 | 5
Build & test scripts to clean up users | 21 | 3
Build & test scripts/process to remove class level portfolio results | 24 | 2
Build & test scripts/process to remove class level index results | 28 | 2
Deliver final package | 30 | 1
Apply in UAT and PROD | 31 | 2
Run upgrade scripts | 35 | 1
Troubleshoot any issue with DEV | 36 | 2
Update scripts to use one common total-level hierarchy for indices | 38 | 2
Build scripts to convert floating-weight benchmark to new functionality | 42 | 3
Build application server | 45 | 2
Install software | 49 | 1
Build latest DB and run upgrade scripts | 50 | 2
Get SS&C assistance (as needed) | 52 | 1
Send updated list of stored procedures to SS&C for confirmation | 53 | 1
Update: pru_syl_port_bench_asof_wrp | 56 | 2
Update: pru_syl_load_memPortBM_PerRolling | 58 | 2
Update: pru_syl_load_cpfactual_mlt | 60 | 2
Update: pru_syl_load_composite_monthly | 64 | 2
Training on like-for-like processes | 66 | 2
Training on new functionality (focus on pain points) | 70 | 2
UAT – run through test scripts | 72 | 5
Update new application server with FIRMRun, Java 21, Autosys | 79 | 2
Reserve Windows 10 boxes for PR team (contingency for Go-Live) | 81 | 1
Update test plan based on Jason's scripts; share with QA | 84 | 2
Setup DB server with SQL Server and supporting software (PROD) | 86 | 2
Setup application server with FIRMRun, Java 21, Autosys (PROD) | 88 | 2
Run processes in parallel | 92 | 5
Provide support as needed (parallel run window) | 99 | 5
Restore test DB on new PROD environment & run upgrade scripts | 106 | 1
Go-Live support | 107 | 3
Hypercare / support for up to 4 weeks post Go-Live | 112 | 20