## Project schedule
| Application Upgrade 7.1 → 7.68 | [5 empty] | Project start: | [7 empty] | 2025-07-03
[7 empty] | Display week: | [7 empty] | 1
[7 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-06-30 to 2025-08-24
 | time axis 2025-06-30 to 2025-08-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Phase 1 – Data Clean Up
| Provide backup of PROD database | PROD-DB | 0% | 2025-07-03 | 2025-07-07 | 5
| Send PROD DB extract to SS&C | PROD-DB | 0% | 2025-07-07 | 2025-07-09 | 3
| Install SQL Server & add users to DEV DB | DEV-DB | 0% | 2025-07-07 | 2025-07-11 | 5
| Request restore of PROD extract into DEV DB | DEV-DB | 0% | 2025-07-14 | 2025-07-15 | 2
| Restore/load PROD extract into DEV DB | DEV-DB | 0% | 2025-07-15 | 2025-07-17 | 3
| Validate data in DEV DB | DEV-DB | 0% | 2025-07-17 | 2025-07-18 | 2
| Install Sylvan 7.68 on DEV App Server | DEV-APP | 0% | 2025-07-21 | 2025-07-23 | 3
| Hand off DEV DB for functional testing | CROSS-ENV | 0% | 2025-07-23 | 2025-07-25 | 3
| Functional testing & cleanup (users/portfolios/indexes) | DEV-DB | 0% | 2025-08-04 | 2025-08-08 | 5
| Environment cleanup | DEV | 0% | 2025-08-04 | 2025-08-08 | 5
| Build/test scripts to clean up users | DEV-DB | 0% | 2025-08-04 | 2025-08-08 | 5
| Build/test scripts to remove class-level portfolio results | DEV-DB | 0% | 2025-08-04 | 2025-08-12 | 9
| Build/test scripts to remove class-level index results | DEV-DB | 0% | 2025-08-04 | 2025-08-12 | 9
| Deliver final cleanup package | CROSS-ENV | 0% | 2025-08-18 | 2025-08-19 | 2
| Apply cleanup in UAT and PROD | UAT/PROD | 0% | 2025-08-20 | 2025-08-22 | 3
| Phase 2 – Upgrade (DEV/Test) | Nuria Acevedo | 25% | 2025-08-23 | 2025-08-27 | 5
| Run DEV upgrade scripts | DEV-DB | 0% | 2025-07-21 | 2025-07-23 | 3
| Troubleshoot DEV issues | DEV | 0% | 2025-07-23 | 2025-07-25 | 3
| Update scripts: single total level hierarchy for indices | DEV-DB | 0% | 2025-07-24 | 2025-08-01 | 9
| Build scripts: convert floating-weight benchmark | DEV-DB | 0% | 2025-07-24 | 2025-08-01 | 9
| Setup DEV / Test Environment | Jens Martensson | 50% | 2025-08-02 | 2025-08-05 | 4
| Build DEV App Server | DEV-APP | 0% | 2025-07-21 | 2025-07-23 | 3
| Install required software | DEV-APP | 0% | 2025-07-23 | 2025-07-25 | 3
| Create latest DEV DB & run upgrade scripts | DEV-DB | 0% | 2025-07-28 | 2025-08-01 | 5
| SS&C assistance (as needed) | VENDOR/SS&C | 0% | 2025-07-21 | 2025-08-01 | 12
Update Custom Reports (Stored Procedures)
| Confirm updated SP list with SS&C | DEV-DB | 0 | 2025-07-28 | 2025-07-29
| pru_syl_port_bench_asof_wrp | DEV-DB | 0 | 2025-07-29 | 2025-07-31
| pru_syl_load_memPortBM_PerRolling | DEV-DB | 0 | 2025-07-30 | 2025-08-05
| pru_syl_load_cfactual_mlt | DEV-DB | 0 | 2025-07-31 | 2025-08-06
| pru_syl_load_composite_monthly | DEV-DB | 0 | 2025-08-01 | 2025-08-08
Training & UAT
| Training: like-for-like processes | ALL/USERS | 0 | 2025-08-18 | 2025-08-20
| Training: new functionality (focus on pain points) | ALL/USERS | 0 | 2025-08-20 | 2025-08-22
| UAT: run test scripts | UAT | 0 | 2025-08-25 | 2025-08-29
Production Environment Setup
| Update new PROD App Server (FIRMRun, Java 21, Autosys) | PROD-APP | 0 | 2025-09-01 | 2025-09-05
| Reserve Windows 10 boxes for Performance Reporting | PROD-APP | 0 | 2025-09-01 | 2025-09-02
| Update test plan & share with QA to develop test plan | QA | 0 | 2025-09-02 | 2025-09-05
| Set up PROD DB Server (SQL Server & supporting SW) | PROD-DB | 0 | 2025-09-08 | 2025-09-12
| Set up PROD App Server (FIRMRun, Java 21, Autosys) | PROD-APP | 0 | 2025-09-08 | 2025-09-12
Parallel Run and Testing
| Run processes in parallel | PROD/DEV | 0 | 2025-09-15 | 2025-09-26
| Provide support as needed (parallel) | TEAM | 0 | 2025-09-15 | 2025-09-26
Go Live
| Restore latest DB on new PROD and run upgrade scripts | PROD-DB | 0 | 2025-10-06 | 2025-10-07
| Application smoke test & support | PROD-APP | 0 | 2025-10-06 | 2025-10-10
Post Go-Live Support
| Hypercare support (up to 4 weeks) | TEAM | 0 | 2025-10-13 | 2025-10-31

## Project Plan
ID | Phase | Workstream | Task Name | Environment | Duration (workdays) | Start | End | Depends On (ID) | Owner | Status | % Complete | Milestone | Notes
1 | Phase 1 – Data Clean Up | Preliminary Work | Provide backup of Sylvan PROD database | PROD | 1 | 2025-07-03 | 2025-07-03 |  |  | Not Started | 0 | No
2 | Phase 1 – Data Clean Up | Preliminary Work | Send Sylvan PROD DB extract to SS&C | PROD | 1 | 2025-07-04 | 2025-07-04 | 1 |  | Not Started | 0 | No
3 | Phase 1 – Data Clean Up | Preliminary Work | Install SQL Server and add all users to Sylvan DEV DB | DEV | 2 | 2025-07-07 | 2025-07-08 | 2 |  | Not Started | 0 | No
4 | Phase 1 – Data Clean Up | Restore PROD data extract → DEV | Submit request to restore/load PROD data extract into DEV Sylvan DB | DEV | 1 | 2025-07-09 | 2025-07-09 | 3 |  | Not Started | 0 | No
5 | Phase 1 – Data Clean Up | Restore PROD data extract → DEV | Restore/Load PROD data extract into DEV Sylvan DB | DEV | 2 | 2025-07-10 | 2025-07-11 | 4 |  | Not Started | 0 | No
6 | Phase 1 – Data Clean Up | Prep & Testing | Check out data in Sylvan DEV DB | DEV | 1 | 2025-07-14 | 2025-07-14 | 5 |  | Not Started | 0 | No
7 | Phase 1 – Data Clean Up | Prep & Testing | Install Sylvan 7.6 upgrade on DEV Sylvan App Server | DEV | 1 | 2025-07-15 | 2025-07-15 | 6 |  | Not Started | 0 | No
8 | Phase 1 – Data Clean Up | Prep & Testing | Hand off Sylvan DEV DB for functional testing (to Jason & team) | DEV | 1 | 2025-07-16 | 2025-07-16 | 7 |  | Not Started | 0 | No
9 | Phase 1 – Data Clean Up | Prep & Testing | Functional testing & cleanup (users, portfolios, indexes) | DEV | 5 | 2025-07-17 | 2025-07-23 | 8 |  | Not Started | 0 | No
10 | Phase 1 – Data Clean Up | Environment Clean Up | Build & test scripts to clean up users | DEV | 3 | 2025-07-24 | 2025-07-28 | 9 |  | Not Started | 0 | No
11 | Phase 1 – Data Clean Up | Environment Clean Up | Build & test scripts/process to remove class level portfolio results | DEV | 2 | 2025-07-29 | 2025-07-30 | 10 |  | Not Started | 0 | No
12 | Phase 1 – Data Clean Up | Environment Clean Up | Build & test scripts/process to remove class level index results | DEV | 2 | 2025-07-31 | 2025-08-01 | 11 |  | Not Started | 0 | No
13 | Phase 1 – Data Clean Up | Environment Clean Up | Deliver final package | DEV | 1 | 2025-08-04 | 2025-08-04 | 12 |  | Not Started | 0 | No
14 | Phase 1 – Data Clean Up | Environment Clean Up | Apply in UAT and PROD | UAT/PROD | 2 | 2025-08-05 | 2025-08-06 | 13 |  | Not Started | 0 | No
15 | Phase 2 – Upgrade | Preliminary Work | Run upgrade scripts | DEV | 1 | 2025-08-07 | 2025-08-07 | 14 |  | Not Started | 0 | No
16 | Phase 2 – Upgrade | Preliminary Work | Troubleshoot any issue with DEV | DEV | 2 | 2025-08-08 | 2025-08-11 | 15 |  | Not Started | 0 | No
17 | Phase 2 – Upgrade | Preliminary Work | Update scripts to use one common total-level hierarchy for indices | DEV | 2 | 2025-08-12 | 2025-08-13 | 16 |  | Not Started | 0 | No
18 | Phase 2 – Upgrade | Conversion Build | Build scripts to convert floating-weight benchmark to new functionality | DEV | 3 | 2025-08-14 | 2025-08-18 | 17 |  | Not Started | 0 | No
19 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Build application server | DEV | 2 | 2025-08-19 | 2025-08-20 | 18 |  | Not Started | 0 | No
20 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Install software | DEV | 1 | 2025-08-21 | 2025-08-21 | 19 |  | Not Started | 0 | No
21 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Build latest DB and run upgrade scripts | DEV | 2 | 2025-08-22 | 2025-08-25 | 20 |  | Not Started | 0 | No
22 | Phase 2 – Upgrade | Setup Sylvan DEV/Test Environment | Get SS&C assistance (as needed) | DEV | 1 | 2025-08-26 | 2025-08-26 | 21 |  | Not Started | 0 | No
23 | Phase 2 – Upgrade | Update Custom Reports | Send updated list of stored procedures to SS&C for confirmation | DEV | 1 | 2025-08-27 | 2025-08-27 | 22 |  | Not Started | 0 | No
24 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_port_bench_asof_wrp | DEV | 2 | 2025-08-28 | 2025-08-29 | 23 |  | Not Started | 0 | No
25 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_load_memPortBM_PerRolling | DEV | 2 | 2025-09-01 | 2025-09-02 | 24 |  | Not Started | 0 | No
26 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_load_cpfactual_mlt | DEV | 2 | 2025-09-03 | 2025-09-04 | 25 |  | Not Started | 0 | No
27 | Phase 2 – Upgrade | Update Custom Reports | Update: pru_syl_load_composite_monthly | DEV | 2 | 2025-09-05 | 2025-09-08 | 26 |  | Not Started | 0 | No
28 | Phase 2 – Upgrade | Training | Training on like-for-like processes | All | 2 | 2025-09-09 | 2025-09-10 | 27 |  | Not Started | 0 | No
29 | Phase 2 – Upgrade | Training | Training on new functionality (focus on pain points) | All | 2 | 2025-09-11 | 2025-09-12 | 28 |  | Not Started | 0 | No
30 | Phase 2 – Upgrade | User Testing | UAT – run through test scripts | UAT | 5 | 2025-09-15 | 2025-09-19 | 29 |  | Not Started | 0 | No
31 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Update new application server with FIRMRun, Java 21, Autosys | PROD | 2 | 2025-09-22 | 2025-09-23 | 30 |  | Not Started | 0 | No
32 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Reserve Windows 10 boxes for PR team (contingency for Go-Live) | PROD | 1 | 2025-09-24 | 2025-09-24 | 31 |  | Not Started | 0 | No
33 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Update test plan based on Jason's scripts; share with QA | PROD | 2 | 2025-09-25 | 2025-09-26 | 32 |  | Not Started | 0 | No
34 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Setup DB server with SQL Server and supporting software (PROD) | PROD | 2 | 2025-09-29 | 2025-09-30 | 33 |  | Not Started | 0 | No
35 | Phase 2 – Upgrade | Setup Sylvan PROD Environment | Setup application server with FIRMRun, Java 21, Autosys (PROD) | PROD | 2 | 2025-10-01 | 2025-10-02 | 34 |  | Not Started | 0 | No
36 | Phase 2 – Upgrade | Parallel Run & Testing | Run processes in parallel | PROD | 3 | 2025-10-03 | 2025-10-07 | 35 |  | Not Started | 0 | No
37 | Phase 2 – Upgrade | Parallel Run & Testing | Provide support as needed (parallel run window) | PROD | 3 | 2025-10-08 | 2025-10-10 | 36 |  | Not Started | 0 | No
38 | Phase 2 – Upgrade | Go Live | Restore test DB on new PROD environment & run upgrade scripts | PROD | 1 | 2025-10-13 | 2025-10-13 | 37 |  | Not Started | 0 | Yes
39 | Phase 2 – Upgrade | Go Live | Go-Live support | PROD | 3 | 2025-10-14 | 2025-10-16 | 38 |  | Not Started | 0 | No
40 | Phase 2 – Upgrade | Post Go Live Support | Hypercare / support for up to 4 weeks post Go-Live | PROD | 10 | 2025-10-17 | 2025-10-30 | 39 |  | Not Started | 0 | No